## Tabelle1
WBS Hammer Time
2018-05-23
Alina, Andreas, Harun, Jaromir
Category | Goal | Task | Department
Hammer Man | movement | implementation | Code
Hammer Man | movement | sprite of Hammer Man moving with hammer over head | Art
Hammer Man | movement | sprite of Hammer Man moving with hammer at high mid height | Art
Hammer Man | movement | sprite of Hammer Man moving with hammer at low mid height | Art
Hammer Man | movement | sprite of Hammer Man moving with hammer at low height | Art
Hammer Man | movement | animation of Hammer Man moving | Art
Hammer Man | movement climb | implementation | Code
Hammer Man | movement climb | sprite of Hammer Man climbing up (right foot up) | Art
Hammer Man | movement climb | sprite of Hammer Man climbing up (right foot down) | Art
Hammer Man | hammer attack | implementation (hit box moves) | Code
Hammer Man | hammer attack | hammer hit enemy sound (umpf!) | Audio
Enemy | movement | implementation | Code
Enemy | movement | enemy moves (left foot forward) | Art
Enemy | movement | enemy moves (right foot forward) | Art
Enemy | movement | animation of enemy moving | Art
Enemy | turn at wall | implementation | Code
Enemy | randomly change direction after fall | implementation | Code
Enemy | spawn and randomly walk left or right | implementation | Code
Enemy | exit level | implementation | Code
Enemy | spawn wave with gaps | implementation | Code
Enemy | counter for how many of the wave are left | implementation | Code
Enemy | counter for how many of the wave are left | bar representing left over enemies | Art
Enemy | enemy deals damage on exit | implementation | Code
Enemy | die on hit | implementation | Code
Level | Layout | design level layout | GD
Level | Layout | apply textures in level | GD
Level | platforms | sprite of a platform | Art
Level | ladders | sprite of a ladder | Art
Level | spawn point | sprite of a spawn point | Art
Level | spawn point | spawn point can be attacked | Code
Level | exit point | sprite of a exit point | Art
Menu Screen | start game button | implementation | Code
Menu Screen | start game button | button design | Art
Menu Screen | exit game button | implementation | Code
Menu Screen | exit game button | button design | Art
Menu Screen | credits button | implementation | Code
Menu Screen | credits button | button design | Art
Credits Screen | credits | credit design | Art
Game Over Screen | retry game button | implementation | Code
Game Over Screen | retry game button | button design | Art
Game Over Screen | exit to menu screen | implementation | Code
Game Over Screen | exit to menu screen | button design | Art
UI | health bar | implementation | Code
UI | health bar | health bar design | Art