## Tabelle1
WBS Hammer Time
2018-05-23
Alina, Andreas, Harun, Jaromir
Category | Goal | Task | Department
Credits Screen | credits | write credit & design | GD
Enemy | movement | animation of enemy moving | Animation
Enemy | movement | enemy moves (left foot forward) | Art
Enemy | movement | enemy moves (right foot forward) | Art
Enemy | movement | implementation | Code
Enemy | turn at wall | implementation | Code
Enemy | randomly change direction after fall | implementation | Code
Enemy | spawn and randomly walk left or right | implementation | Code
Spawner | spawn enemies every x time public float | implementation | Code
Spawner | pause spawning for x time public float | implementation | Code
Enemy | deals damage to population health on exit | implementation | Code
Enemy | die on hit | implementation | Code
Game Over Screen | retry game button | button design | Art
Game Over Screen | exit to menu screen button | button design | Art
Game Over Screen | retry game button | implementation | Code
Game Over Screen | exit to menu screen button | implementation | Code
Hammer Man | movement | animation of Hammer Man moving | Animation
Hammer Man | movement climb | animate Hammer Man going upstairs | Animation
Hammer Man | movement | sprite of Hammer Man moving with hammer over head | Art
Hammer Man | movement | sprite of Hammer Man moving with hammer at high mid height | Art
Hammer Man | movement | sprite of Hammer Man moving with hammer at low mid height | Art
Hammer Man | movement | sprite of Hammer Man moving with hammer at low height | Art
Hammer Man | movement climb | sprite of Hammer Man going upstairs (right foot up) | Art
Hammer Man | movement climb | sprite of Hammer Man going upstairs (left foot up) | Art
Hammer Man | hammer attack | hammer hit enemy sound (umpf!) | Audio
Hammer Man | hammer attack | implement hammer hits ground sound | Audio
Hammer Man | movement | implementation move left and right | Code
Hammer Man | movement climb | implementation going upstairs | Code
Hammer Man | movement jump down platform | implementation (S button makes Hammer Man fall through platform) | Code
Hammer Man | hammer attack | implementation (hit box moves, strike active time) | Code
Level | platforms | texture of a platform | Art
Level | ladders | sprite of a ladder | Art
Level | spawner | sprite of a spawner | Art
Level | door (exit point) | sprite of a door | Art
Level | spawner | spawner can be attacked and destroyed | Code
Level | layout | design level layout | GD
Level | layout | apply textures in level | GD
Level | game over state | switch to game over screen when health hits zero | Code
Menu Screen | start game button | button design | Art
Menu Screen | exit game button | button design | Art
Menu Screen | credits button | button design | Art
Menu Screen | start game button | implementation | Code
Menu Screen | exit game button | implementation | Code
Menu Screen | credits button | implementation | Code
UI | health bar spawner | implementation (spawner health + health bar) | Code
UI | health bar population | health bar design | Art
UI | health bar population | implementation | Code