## Tabelle1
WBS Hammerjaeger
2018-06-04
Alina, Andreas, Harun, Jaromir
Category | Goal | Task | Department | Progress
Credits Screen | credits | write credit & design | GD
Enemy | movement | animation of enemy moving | Animation
Enemy | movement | enemy moves sprites | Art
Enemy | movement | implementation | Code
Enemy | turn at wall | implementation | Code
Enemy | randomly change direction after fall | implementation | Code
Enemy | spawn and randomly walk left or right | implementation | Code
Spawner | spawn enemies every x time public float | implementation | Code
Spawner | pause spawning for x time public float | implementation | Code
Enemy | deals damage to population health on exit | implementation | Code
Enemy | die on hit | implementation | Code
Game Over Screen | retry game button | button design | Art
Game Over Screen | exit to menu screen button | button design | Art
Game Over Screen | retry game button | implementation | Code
Game Over Screen | exit to menu screen button | implementation | Code
Hammerjaeger | movement | animation of Hammerjaeger moving | Animation
Hammerjaeger | movement climb | animate Hammerjaeger going upstairs | Animation
Hammerjaeger | movement | sprites of Hammerjaeger moving while hammering | Art
Hammerjaeger | standing | sprites of Hammerjaeger standing while hammering | Art
Hammerjaeger | movement climb | sprite of Hammerjaeger climbing up | Art
Hammerjaeger | hammer attack | hammer hit enemy sound (umpf!) | Audio
Hammerjaeger | hammer attack | implement hammer hits ground sound | Audio
Hammerjaeger | movement | implementation move left and right | Code
Hammerjaeger | movement climb | implementation going upstairs | Code
Hammerjaeger | movement jump down platform | implementation (S button makes Hammerjaeger fall through platform) | Code
Hammerjaeger | hammer attack | implementation (hit box moves, strike active time) | Code
Level | platforms | texture of a platform | Art
Level | ladders | sprite of a ladder | Art
Level | spawner | sprite of a spawner | Art
Level | door (exit point) | sprite of a door | Art
Level | spawner | spawner can be attacked and destroyed | Code
Level | layout | design level layout | GD
Level | layout | apply textures in level | GD
Level | game over state | switch to game over screen when health hits zero | Code
Menu Screen | start game button | button design | Art
Menu Screen | exit game button | button design | Art
Menu Screen | credits button | button design | Art
Menu Screen | start game button | implementation | Code
Menu Screen | exit game button | implementation | Code
Menu Screen | credits button | implementation | Code
UI | health bar spawner | implementation (spawner health + health bar) | Code
UI | health bar population | health bar design | Art
UI | health bar population | implementation | Code
Category | Goal | Task | Department | Progress
Disruptive Enemy | exploding enemy | animation of exploding enemy moving | Animation
Disruptive Enemy | exploding enemy | animation of explosion blast | Animation
Disruptive Enemy | resurrectable enemy | animation of resurrectable enemy moving | Animation
Disruptive Enemy | two sided enemy | animation of two sided enemy moving | Animation
Disruptive Enemy | two sided enemy | animation of the halves of the enemy moving | Animation
Disruptive Enemy | one sided enemy | animation of one sided enemy moving | Animation
Disruptive Enemy | armoured enemy | animation of armoured enemy moving | Animation
Disruptive Enemy | armoured enemy | animation of armour breaking | Animation
Disruptive Enemy | spawning enemy | animation of spawning enemy moving | Animation
Disruptive Enemy | toss-able enemy | animation of toss-able enemy moving | Animation
Disruptive Enemy | exploding enemy | sprites of exploding enemy moving | Art
Disruptive Enemy | resurrectable enemy | sprites of resurrectable enemy moving | Art
Disruptive Enemy | resurrectable enemy | sprite of "dead" resurrectable enemy | Art
Disruptive Enemy | two sided enemy | sprites of two sided enemy moving | Art
Disruptive Enemy | one sided enemy | sprites of one sided enemy moving | Art
Disruptive Enemy | armoured enemy | sprites of armoured enemy moving | Art
Disruptive Enemy | spawning enemy | sprites of spawning enemy moving | Art
Disruptive Enemy | toss-able enemy | sprites of toss-able enemy moving | Art
Disruptive Enemy | exploding enemy | enemy that explodes a short time after being hit and knocks Hammerjaeger 2 platforms up or down (randomly or where there is space respectively) | Code
Disruptive Enemy | resurrectable enemy | enemy that can be revived after hit by other enemy passing by OR completely destroyed after two hits | Code
Disruptive Enemy | two sided enemy | enemy that can only be destroyed when hit once from the front and once from the back AND walkes in the opposite direction than it has been hit from | Code
Disruptive Enemy | one sided enemy | enemy that can only be hit from ONE specific side | Code
Disruptive Enemy | armoured enemy | enemy that can only be destroyed when Hammerjaeger jumped before the hammer hits him (jump attack) | Code
Disruptive Enemy | spawning enemy | enemy that spawns two regular enemies when hit | Code
Disruptive Enemy | toss-able enemy | enemy that is knocked back into the direction that it has been hit from AND can only die when it is hit into a wall | Code
Hammerjaeger | movement jump | animation of Hammerjaeger jumping | Animation
Hammerjaeger | movement jump | sprites of Hammerjaeger jumping while hammering | Art
Hammerjaeger | hammer attack | feedback effects | Art
Hammerjaeger | hammer attack | feedback effects | Audio
Hammerjaeger | movement jump | Hammerjaeger jumps | Code
Level | background | sprite of a wallpaper tile | Art
Level | background | sprite of a brick wall tile | Art
Level | background | sprite of a wooden panelling tile | Art
Level | destructible furniture | furniture objects can be set to a destroyed state and are furthermore no longer interactable | Code
Supportive Enemy | trap enemy | animation of trap enemy moving | Animation
Supportive Enemy | repairing enemy | animation of repairing enemy moving | Animation
Supportive Enemy | repairing enemy | animation of repaqiring enemy repairing the door | Animation
Supportive Enemy | shock wave enemy | animation of shock wave enemy moving | Animation
Supportive Enemy | shock wave enemy | animation of shock wave | Animation
Supportive Enemy | trap enemy | sprites of trap enemy moving | Art
Supportive Enemy | trap enemy | sprite of trap | Art
Supportive Enemy | repairing enemy | sprites of repairing enemy in normal mode moving | Art
Supportive Enemy | repairing enemy | sprites of repairing enemy in repair mode moving | Art
Supportive Enemy | shock wave enemy | sprites of shock wave enemy moving | Art
Supportive Enemy | trap enemy | enemy that becomes a trap for x amount of enemies after been hit | Code
Supportive Enemy | repairing enemy | not destroyed when hit but instead rebuilds/repairs exit door by one HP when it gets there and destroys itself after | Code
Supportive Enemy | shock wave enemy | enemy that when hit creates a shock wave that hits all enemies on the same platform | Code